## Sheet1
Sl No | Workstream | Tasks/Activities | Start Week | End Week | Acceptance Criteria | RACI | Dependencies | Issues/Constraints | Person Days | Skill Requirements | Sign-off Authority | Location of Delivery
1 | Governance & Stakeholder Management | Establish governance framework, define roles, conduct meetings, manage compliance | 1 | 20 | Governance meetings completed, compliance validated | R: PM, A: CIO, C: IT Leadership, I: Business Units | Leadership approvals, business alignment | Time zone challenges, regulatory constraints | 30 | Program Management, Compliance | CIO | Remote
2 | IT Due Diligence & Assessment | Assess IT infrastructure, identify risks, document findings | 1 | 4 | IT risk assessment report completed, findings documented | R: IT Security, A: CIO, C: Compliance Team, I: Business Units | Availability of IT SMEs, vendor input | Legacy system complexities, compliance | 20 | IT Security, Compliance | CIO | Remote
3 | Identity & Access Management (IAM) Integration | Migrate Office 365 & AD, align access policies, user training | 5 | 14 | User accounts migrated successfully, minimal downtime | R: IAM Lead, A: IT Director, C: Business Units, I: IT Security | User data readiness, cloud policies | GDPR constraints, legacy authentication | 40 | IAM, Security, Microsoft AD | IT Director | Remote & Onsite
4 | Network & Security Standardization | Standardize network (Cisco, Fortinet), implement security policies, audits | 5 | 14 | Network security compliance achieved, no major incidents | R: Network Team, A: CISO, C: Business Units, I: IT Security | Vendor collaboration, IT infrastructure | Legacy firewall configurations, bandwidth issues | 50 | Network Engineering, Security | CISO | Hybrid
5 | Endpoint & PC Standardization | Standardize OS, software, deploy security tools, continuity check | 5 | 14 | PCs operational with standard configurations, secure endpoints | R: IT Support, A: IT Director, C: Business Units, I: Security | Hardware procurement, image deployment | Supply chain delays, user resistance | 40 | IT Support, Security | IT Director | Onsite
6 | Application & Data Migration | Assess apps, execute Lift & Shift, validate data, implement rollback | 6 | 16 | Applications running smoothly post-migration, no data loss | R: App Migration Lead, A: CIO, C: Business Units, I: IT Support | Vendor dependencies, cloud readiness | Data loss risks, integration failure | 60 | Cloud Migration, Database | CIO | Hybrid
7 | Business Process Alignment & Change Management | Align IT processes, train users, monitor adoption | 6 | 20 | Users trained, process adoption above 90% | R: Change Manager, A: IT Director, C: Business Units, I: HR | Business alignment, change adoption | User resistance, compliance adherence | 30 | Change Management, Training | IT Director | Remote & Onsite
8 | Post-Integration Support & Optimization | Monitor performance, resolve issues, finalize handover | 15 | 20 | Performance stabilized, no major post-integration issues | R: IT Ops, A: CIO, C: Business Units, I: Security | Resource availability, system monitoring | Long-term support gaps, business feedback | 20 | IT Operations, Optimization | CIO | Hybrid